## Slide 1: Data Architecture: Progress against milestone plan for Polaris 1.0
2018
2019
2020
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
  Red-test security audit by
  (third parties)
  Evaluate and implement compute engine
  Connect directly to sources (beyond EDW)
Environment design and build
  Establish v 1.0 of data governance structure
  Sequentially implement data model by domain
  Refine & extend model for new use cases
  DataOps tool selection
  Define high-level domain model
  Document cyber control framework and plan (Optiv)
  Design capabilities reference architecture
  Evaluate/complete initial tool selection
  Establish data flows to support lighthouses
Activity
Phase I: complete technical design, establish test platform
Phase II: industrialize platform for initial lighthouses
Phase III: harden and extend to additional use cases
Not started
In progress
Complete
Progress legend
  Evaluate and begin MDM implementation
  Stabilize, harden, expand platform
Data Management
  Continue to harden Data Security & Governance
Data Governance and Security
  Design & implement initial security architecture
  Stand up initial cloud environment
Polaris 1.0 Go Live
  Design v1.0 of canonical data model
To be determined: Timeline to incorporate Sonic into platform
  Implement PII Data security controls
  (Milestone I)
  Enable Customer and Menu Master in MDM
  Canonical Model implemented for all Domains
  Enable security controls for 2 Use Cases (Milestone II)
  Enable broader Polaris Access controls (Milestone III)
  Enable controls for external app access (Milestone IV)
  Additional tool selection

## Slide 2: Platform: Reference Architecture
Sources
Data platform
Data Consumption
Data security
Meta-data
MDM
Data modeling
Workflow mgt.
Container mgt.
Code versioning
CI / CD1
Batch data DB
EDW / Data Marts
Real-time data DB
MDM DB
Data Lake
Sys Ops
Ingestion Layer
Logic and Compute Layer
Storage Layer
Data Mgt
Data Ops
Data Sources
Transformation
Validation
Quality checks
Real-time Ingest
API mgt.
Batch Ingest
Data Connectors
Omni-channel e-commerce (e.g. app, website, kiosk)
Non-commercial front-end (e.g. loyalty profile, social media)
3rd party data (e.g. weather, outsourced capabilities)
Restaurant tech (e.g. POS, KDS, DTT, BoH BOS)
Digital Channels2 (e.g. apps and marketing data)
Not started
In progress
Complete
Progress legend
Use case Models
Digital Marketing
BI Dashboards
Visualization
Ops reporting
Reporting & BI
Advanced Analytics
Marketing
Apps (Mobile, Web)
B/O tools and apps
Back-office
Future capability
Data Integration

## Slide 3: EDW & BDW Migration Options
"Single pane of glass" for Analytics / Insight teams
Consolidated reporting capabilities
165 Reports
Onboard downstream users
13.5 TB of Data
Change Management
Accelerate Polaris value delivery
Eliminate Data Security risks from EDW
Eliminate investment required to keep legacy platform/s online
Ease of Data Access to consuming applications
20 Data Sources
700+ processes
13 external app integration
6 internal app integration
Option A
(Complete EDW migration to Polaris)
Option B
(Integrate Legacy Platforms with Polaris as interim solution)
Option C
(Do not migrate)
Scope
Business Value
$6.0MM
$ TBD
$ 0
High Value, High Cost, Longer duration option
Carries risk due to size and complexity when taken into account other large-scale initiatives at Inspire
Implication :
$1.5MM/year operation cost avoidance won’t be realized until the full migration
Assumes limitations of legacy systems performance and stability
Mitigates risk given other large-scale projects
Less disruption for users compared to Option A
Implication :
All Implications of Option B
AND
Continued poor user experience from having to use multiple platforms.
Inability to access cross Brand data from a single location